## Migration Planning
Task # | Task | Dependency | Assignee | Start Date | End Date | Comments | Status | Pct Completion | AzDO Ref #
| Developer workstation with development tools |  |  | 2022-07-20 | 2022-08-08
| Review existing technical design, build release pipelines |  |  | 2022-07-20 | 2022-08-12
Milestone | Workstation Setup Complete
| SVN to Git Source Code Migration |  |  | 2022-07-29 | 2022-08-12 | Completed
| Create plan for SVN cutover to Git |  |  | 2022-07-29 | 2022-08-12 | Completed
| Install tools needed to support migration |  |  | 2022-07-20 | 2022-08-02 | Completed
| SVN to Git Migration using SVN2Git tool |  |  | 2022-07-29 | 2022-08-12 | Completed
| combine LS_DS_WAR and TS_JAR SVN Repo into new project TS_LS_DEPS |  |  | 2022-07-29 | 2022-08-12 | Completed
| Push repository to DevOps |  |  | 2022-07-29 | 2022-08-12 | Completed
| Convert TeamCity pipelines to use Git repository for builds (10 projects) |  |  | 2022-07-29 | 2022-08-12 | Completed
| Migrate users to use LDAP instead of the OS users. |  |  | 2022-09-18 | 2022-09-25 | Need more information from Chris
| Convert Custom LSCS API to DocumentDB |  |  | TBD | TBD | Phase 2 - Clarification - dependency on AWS provision of DocumentDB
Milestone | Refactoring Complete (Cloud, Container, Security) |  |  | 2022-07-20 | 2022-09-25
| Ensure Unit test code coverage |  | TBD | TBD | TBD | Working with Srikanth to get a QA assigned to the project
| Implement generic logging solution |  | TBD | TBD | TBD | Working with Srikanth to get a QA assigned to the project
Milestone | Unit Test Code Coverage Complete
| Clarification on "phases" of the migration to AWS - 1. Runtime 2. Authoring 3. Version upgrade |  |  | 2022-08-12 | 2022-08-18
| Clarification on converstion of custom LSCS to DocumentDB |  |  | 2022-08-18 | TBD | Phase 2 - Clarification - dependency on AWS provision of DocumentDB
| Determine TeamSite Multi-AZ setup | AWS DEV environment provisioning |  | 2022-08-22 | TBD | Requirement/clarificayions are in progress. Amy & Stephen
| Determine strategy for TBs of files from on-prem to EFS drive |  |  | TBD | TBD | Need to check with Sam,Kamlesh & Cloud team
Milestone | Discovery Activities Complete |  |  | 2022-08-12 | 2022-08-18
| Collaborate with CloudServices Team to Provision Cloud Resources - DEV | Architecture Approval |  | 2022-08-22 | 2022-09-02 | Completed
| Provision DEV environment - Authoring AWS environment - TeamSite/OpenDeploy |  |  | 2022-08-22 | 2022-09-15 | EC2 has been provisioned.Dependencies has been installed.
| Collaborate with CloudServices Team to create TeamSite/OpenDeploy disaster recovery environment |  |  | 2022-08-29 | 2022-09-18 | Template Shared with provisioning team.Prov in process
Milestone | Provision AWS Cloud Resources for TeamSite (Phase1) |  |  | 2022-08-22 | 2022-09-18
| Collaborate with CloudServices Team to Provision Cloud Resources - DEV | Architecture Approval |  | TBD | TBD
| Provision DEV environment - OpenDeploy Receiver, Runtime AWS environment - LiveSite Web NGINX and App Tomcat Services, and DocumentDb replacement for custom LSCS |  |  | TBD | TBD | Amy collecting the requirements to raise a request.
Milestone | Provision AWS Cloud Resources for LiveSite (Phase2)
| Collaborate with CloudServices Team to Provision Cloud Resources - DEV |  |  | TBD | TBD | Dependent on phase 2 completion
| Provision DEV environment - updated services -- postgreSQL, EC2 instance, etc |  |  | TBD | TBD | Dependent on phase 2 completion
Milestone | Provision AWS Cloud Resources for LiveSite (Phase3) |  |  | TBD | TBD
| Create Build & release pipeline.(Utilized for Dev,Stag & Prod) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD | Build pipeline is being migrated to AzDo.Updates in progress.Discussion for Mavern vs Ant in progress(Chris/Amy)
| Collaborate with CloudServices Team to Provision Cloud Resources - STAG | Provision AWS Cloud Resources for TeamSite | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD | Dependency on Dev env provisioning
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (DEV) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD | Dependency on Dev env provisioning
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (STAG ) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD | Dependency on Dev env provisioning
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (PROD ) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD | Dependency on Dev/Stag env provisioning
| Work with CloudServices team to provision security and user groups/roles for developers and administrators |  | Adil Mirza,Venkat Raman,Amy | 2022-09-01 | TBD
Milestone | Provision Release Pipelines Resources for TeamSite (Phase 1) |  |  | 2022-09-01 | TBD
| Create build & release pipeline for Phase 2 |  | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
| Collaborate with CloudServices Team to Provision Cloud Resources - STAG | Provision AWS Cloud Resources for LiveSite | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (DEV) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (STAG ) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
| Create / Update infrastructure release application pipelines to provision cloud infrastructure for all environments (PROD ) |  | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
| Work with CloudServices team to provision security and user groups/roles for developers and administrators |  | Adil Mirza,Venkat Raman,Amy | 2022-09-05 | TBD
Milestone | Provision Release Pipelines Resources for LiveSite (Phase 2) |  |  | 2022-09-05 | TBD
| Update infrastructure release application pipelines to provision cloud infrastructure for all environments (DEV) |  | Adil Mirza,Venkat Raman,Amy | TBD | TBD
| Update infrastructure release application pipelines to provision cloud infrastructure for all environments (STAG ) |  | Adil Mirza,Venkat Raman,Amy | TBD | TBD
| Update infrastructure release application pipelines to provision cloud infrastructure for all environments (PROD ) |  | Adil Mirza,Venkat Raman,Amy | TBD | TBD
Milestone | Update Release Pipeline Resources for Phase 3
| Define related configurations (Secrets) and update the secret manager accordingly |  | Tony,Spephan,Amy | 2022-09-08 | TBD
Milestone | Environments ready for deployment
| Complete Security Profile within SD Elements (Survey) |  | Vishal,Amy | NA | NA | As per Victoria it may not be required.Amy to reply to Victoria for clarification
| Closure of SD Element comments |  | Vishal,Amy | NA | NA
| Pipeline updates for Veracode scans |  | Adil,Venkat | 2022-09-18 | 2022-09-25
| Run AppScan/Veracode - Dynamic Analysis Scan (STAGE) |  | Vishal,Amy | TBD | TBD | Need to make sure pipeline are updated after Stag is up.
| Review the System Architecture with InfoSec team |  | Vishal,Amy | 2022-08-18 | 2022-08-18 | Completed
| Veracode Vulnerability (Remediation Efforts) |  | Vishal,Amy | TBD | TBD | Once Stag is up & piplelines arte update. we can start.
| Work with NYC3 (NYC Cyber Command Center) and DoITT InfoSec teams to complete Security Accreditation process |  | Vishal,Amy | TBD | TBD
Milestone | Security Accredition Complete |  |  | TBD | TBD
| Convert Oracle HTTPS Configuration to NGINX |  |  |  |  | Is containerization and NGINX configuration part of the pipeline
Dockerize Webserver (NGINX) deployment
| Convert Weblogic App server configuration to Tomcat |  |  |  |  | Is containerization and Tomcat configuration part of the pipeline
Dockerize Appserever (Tomcat) deployment
AWS DevOps & Pipeline Set Up
Migrate application source code to Azure Devops
Setup the DevOps Chains
Create a build pipeline
Milestone | Updates to Build Pipelines Completed
Implement Cloud Credential & Certificate Management within Release Pipelines
Create application release pipelines to deploy the application for all environments
Integrate with SonarQube
Integrate with Veracode (Static Scan)
Milestone | Updates to Release Pipelines Ready
DB Infrastructure/Migration task for DEV (TeamSite Authoring)
DB Infrastructure/Migration task for STAG (TeamSite Authoring)
DB Infrastructure/Migration task for PROD (TeamSite Authoring)
Gage the Size of PROD Database Data (Ask Philip)
Enable Native Network Encryption/TDE for column level Encryption(Dev/STAG)
Enable Native Network Encryption/TDE for column level Encryption(Prod)
TeamSite DBA ACL List (Dev) - Teamsite
TeamSite DBA ACL List (STAG) - Teamsite
TeamSite DBA ACL List (Prod) - Teamsite
Create Master DB User and App DB User Accounts in the Database(Dev) - Teamsite
Create Master DB User and App DB User Accounts in the Database(STAG) - Teamsite
Create Master DB User and App DB User Accounts in the Database(Prod) -Teamsite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(Dev) - -Teamsite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(STAG) - -Teamsite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(Prod) - -Teamsite
Export the data from existing Prod Database (Migrate using the tool)(ON-PREM) & Import the data to the Database (Migrate using the tool) to AWS
Run the script to Clean up test Data (STAG)
Referesh prod data during cutover
TeamSite FileShare data migration
Milestone | Application Data Migration Complete (DEV, STAG, PROD) TeamSite Phase 1
DB Infrastructure/Migration task for DEV (LiveSite)
DB Infrastructure/Migration task for STAG(LiveSite)
DB Infrastructure/Migration task for PROD(LiveSite)
Gage the Size of PROD Database Data (Ask Philip)
Enable Native Network Encryption/TDE for column level Encryption(Dev/STAG)
Enable Native Network Encryption/TDE for column level Encryption(Prod)
LiveSite DBA ACL List (Dev) -LiveSite
LiveSite DBA ACL List (STAG) - LiveSite
LiveSite DBA ACL List (Prod) - LiveSite
Create Master DB User and App DB User Accounts in the Database(Dev) - LiveSite
Create Master DB User and App DB User Accounts in the Database(STAG) - LiveSite
Create Master DB User and App DB User Accounts in the Database(Prod) - LiveSite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(Dev) - LiveSite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(STAG) - - LiveSite
Create Master DB User and App DB User Accounts credentials on Secrets Manager(Prod) - -LiveSite
Export the data from existing Prod Database (Migrate using the tool)(ON-PREM) & Import the data to the Database (Migrate using the tool) to AWS
Run the script to Clean up test Data (STAG)
Referesh prod data during cutover
LiveSite Webserver fileshare data migration
LiveSite LSDS AppServer fileshare data migration
LiveSite LSCS data migration - DocumentDB
Milestone | Application Data Migration Complete (DEV, STAG, PROD) LiveSite Phase 2
Application User Provisioning (Devops Team)
Identify Users and User Groups / Security Profiles to be migrated / created for developer users
Work with CloudServices team to provision security and user groups/roles
Milestone | User Provisioning Complete
Load Balancer / DNS / SSL Certificates Activities
Work with Network team to make firewall changes for external service access (inform InfoSec afterwards)
Request ITSecOps to sign the Internal SSL certificate
Request for external Load Balancer and a DNS record for PROD environment
Ensure that Staging and Production environments are identical from a Firewall Perspective
Test the TeamSite service connectivity from App(STAG)
Test the TeamSite service connectivity from App(Prod)
Request for CNAME (Internal) and redirect to Internal Load Balancer
Ensure SSL Mechanism works in the DEV Environment.
Milestone | LB / DNS / SSL Certificates Complete
Integrate Monitoring Services and create Cloudwatch Dashboard (AWS)- STAG
Integrate Monitoring Services,Health Check and create Cloudwatch Dashboard -(new product call Thousand-Eyes - In PROD only) , X-Ray Monitoring
Integrate Monitoring Services - Incident Management - ServiceNow [PROD Only] - POST Deployment Activity
Integrate Application logs with CloudWatch Stack (Cloud)
Enable notifications for application monitoring [PROD ONLY] - Post PROD Deployment Activity
Security Review (Venkata & Vishal)
Milestone | Monitoring, Security and Management Complete
Organizational Reviews
Technical Design Peer Review
Operational Design Review
| Security Review (Venkata & Vishal) - Chris Set it up with the respective team |  | Amy | 2022-08-18 | 2022-08-18
Milestone | Reviews Complete
TeamSite Documentation
Create/Update Architecture Document (Draw.io integrates with Office 365)
Create/Update Development Technical Design Document on AppDev wiki
Create/Update the Operational Design Document on AppDev Wiki (Sharepoint)
Milestone | Documentation Complete
Application Testing & QA Procedures (Automation)
Create QA Automation Scripts
Perform Functional & Integration Testing
Link Test Cases to AZDO User Stories (Angela's Method)
Milestone | Functional / Integration Testing Complete
Create Performance Test Scripts & Pipelines
Perform Performance Testing
Milestone | Performance Testing Complete
Develop UAT Test Scripts and work with business stakeholders
Perform UAT (All Agencies)
Milestone | UAT / ADA Complete
Deploy to STAGING (Checklist)
Provision/Deploy Staging environment
Make Staging Database available
Deploy Application into Staging Environment
Establish Staging Environment URL
Monitoring Tools integration (Cloud Watch-Done, ServiceNow(Do we need this on Prod - Tony?), Monitoring Dashboards-Done) - Staging Environment
Perform Data Migration of TeamSite STG DB
Run fileshare data migration for TeamSite STG
Dynamic Security Scan
Security Scan & Remediation
Execute functional and automated test cases in Staging
Security Accreditation Document
Conduct the meeting for Security Review
Application Security Review - Final
Performance Testing (QA - Kishor)
QA Reviews / Testing/ Approvals
Business Owner Notification to perform UAT
UAT
Milestone | Staging Complete
Deploy to Production (Implementation / Cutover)
Plan the implementation / cutover to new application on AWS
Production Env Setup
Determine the database configurations and enable the configurations in all Environments
Modify provisioning pipelines to enable database configuration decisions
Make Production Database Available with encryption
Monitoring Tools integration (Cloud Watch, ServiceNow, Monitoring Dashboards) - Prod Environment
Update the Implementation Plan
Achieve Change Control Board Approval
Execute the Cutover (includes any final data migration)
Perform Data Migration of LiveSite PRD DB - Phase 2
Perform Data Migration of TeamSite PRD DB - Phase 1
Run fileshare data migration for TeamSite Prod - Phase 1
Run fileshare data migration for LiveSite Web Prod - Phase 2
Run fileshare data migration for LiveSite App Prod - Phase 2
| Dry Run of Cutover |  |  | 2022-12-08 | 2022-12-08
Shut down on-prem TeamSite - Phase 1
Shut down on-prem LiveSite - Phase 2
Milestone | Implementation / Cutover
Post Production Support
Post Production - Need to update operation Standard Operating Procedures
Milestone | Post Production Operations - Operational
Formulas:
Start Date = MIN(E5:[Start Date, row above])
End Date = MAX(F5:[End Date, row above])

## KeyDefinitions
Task | Description | Progress Notes
Project Planning | High level project planning. Excludes ongoing sprint planning
Requirements | Migrating requirements to AzDO and/or creation of new user stories | % of total number of expected user stories
Architecture | Prepare architecture diagram and Data Flow diagram, complete reviews | 100% completion after external review is done and approved.
​Technical Design Review | Technical peer review and Operational peer review | 50% for one, 100% after both complete
Security Profiling | SD Elements profile creation and responding to all questions
Security Accreditation | Security remediation completion and exception approval if required
Coding | Application modernization including unit testing
Data Migration | Data migration for dev, stage and prod | 33% for each environment completion
Dev Infrastructure | Stand up development infrastructure
CI/CD Pipeline | Build / release pipelines completed for Dev
Test Cases | Functional and automation test case development | % of total number of expected test cases
App Deployment to Dev | Application successfully deployed to development
Staging and Prod Infrastructure | Stand up stage and prod infrastructure | 50% for one, 100% after both complete
Monitoring Configuration | Set up monitoring and dashboards for dev, stage and prod | 33% for each environment completion
App Deployment to Staging | Application successfully deployed to stage
App Testing | Functional and automated test execution
Performance Testing | Performance testing on stage
UAT | User acceptance test execution
​QA Signoff | Signoff from QA for user stories and test cases | Binary, 0% or 100%
Production Cutover | Production deployment and cutover | Binary, 0% or 100%

## ProjectMilestones
Task # | Tasks | Dependency | Assignee | Start Date | End Date | Comments | Status | Pct Completion | AzDO Ref #
| Discovery Completed |  |  | 2022-08-01 | 2022-09-21
| Resources identified & assigned |  |  | 2022-08-01 | 2022-09-21
| Migration plan completed |  |  | TBD | TBD
MileStone | Project Planning Completed |  |  | 2022-08-01 | 2022-09-21
| Functional stories created in AzDo |  |  | 2022-08-01 | 2022-08-21
| Enabler Stories Created in Azdo |  |  | 2022-08-15 | 2022-08-30
| Story Review completed |  |  | 2022-09-15 | 2022-09-26
Milestone | Requirements Completed |  |  | 2022-08-01 | 2022-09-26
| Prepare Architecture Diagram & flows |  |  | 2022-08-01 | 2022-08-15
| Internal Reviews of Arch Diag |  |  | 2022-08-16 | 2022-08-19
| Security Review & approval of Arch diag |  |  | 2022-08-20 | 2022-08-27
MileStone | Architecture Completed |  |  | 2022-08-01 | 2022-08-27
| Design wiki updates |  |  | 2022-08-15 | 2022-11-03
| Design wiki peer Review | Design wiki updates |  | 2022-11-04 | 2022-11-08
| Operation details added to design wiki | UAT |  | 2022-11-02 | 2022-11-04
MileStone | ​Technical Design Review Completed |  |  | 2022-08-15 | 2022-11-08
| Survery completed |  |  | 2022-08-15 | 2022-08-30
| Security profile created(SDE) |  |  | NA | NA
| Complete all the items in Security profile |  |  | NA | NA
MileStone | Security Profiling |  |  | 2022-08-15 | 2022-08-30
| Veracode scan completed | App Deployment to Staging |  | 2022-11-03 | 2022-11-14
| Risk document completion | Veracode scan completed |  | 2022-11-15 | 2022-11-17
| SDE Elements closure |  |  | NA | NA
| Approval & Signoff Acquired | App Deployment to Staging Veracode scan completed |  | 2022-11-18 | 2022-11-23
MileStone | Security Accreditation Completed
| Update the code for Phase 1 | Application deployment to Dev - Phase 1 |  | 2022-09-30 | 2022-10-11
| Update the code for Phase 2 | Application deployment to Dev - Phase 2 |  | 2022-10-13 | 2022-10-24
| Update the code for Phase 3 | Application deployment to Dev - Phase 3 |  | 2022-10-24 | 2022-11-02
MileStone | Coding |  |  | 2022-09-30 | 2022-11-02
| Database infrastructure for Phase1 including TDE,ACL,Master DB /App DB user setup(Dev) | Dev Infrastructure ready including installation,update & Database for phase 1 |  | 2022-09-20 | 2022-09-23
| Migrate data from on-prem to AWS Phase 1 (Dev) | Dev Infrastructure ready including installation,update & Database for phase 1 |  | 2022-09-20 | 2022-09-23
| Database infrastructure for Phase1 including TDE,ACL,Master DB /App DB user setup(Stag) | Infrastructure setup for Phase 1(Stag) |  | 2022-10-10 | 2022-10-13
| Migrate data from on-prem to AWS Phase 1 (Stag) | Infrastructure setup for Phase 1(Stag) |  | 2022-10-10 | 2022-10-13
| Database infrastructure for Phase1 including TDE,ACL,Master DB /App DB user setup(Prod) | Infrastructure setup for Phase 1(Prod) |  | 2022-10-10 | 2022-10-13
| Migrate data from on-prem to AWS Phase 1 (Prod) | Infrastructure setup for Phase 1(Prod) |  | 2022-10-10 | 2022-10-13
| Database infrastructure for Phase2 including TDE,ACL,Master DB /App DB user setup(Dev) | Dev Infrastructure ready including installation,update & database for phase 2 |  | 2022-10-03 | 2022-10-06
| Migrate data from on-prem to AWS Phase 2(Dev) | Dev Infrastructure ready including installation,update & database for phase 2 |  | 2022-10-03 | 2022-10-06
| Database infrastructure for Phase2 including TDE,ACL,Master DB /App DB user setup(Stag) | Infrastructure setup for Phase 2(Stag) |  | 2022-10-21 | 2022-10-26
| Migrate data from on-prem to AWS Phase 2(Stag) | Infrastructure setup for Phase 2(Stag) |  | 2022-10-21 | 2022-10-26
| Database infrastructure for Phase2 including TDE,ACL,Master DB /App DB user setup(Prod) | Infrastructure setup for Phase 2(Prod) |  | 2022-10-21 | 2022-10-26
| Migrate data from on-prem to AWS Phase 2(Prod) | Infrastructure setup for Phase 2(Prod) |  | 2022-10-21 | 2022-10-26
| Database infrastructure for Phase3 including TDE,ACL,Master DB /App DB user setup(Dev) | Dev Infrastructure ready including installation,update & Database for phase 3 |  | 2022-10-12 | 2022-10-17
| Migrate data from on-prem to AWS Phase 3(Dev) | Dev Infrastructure ready including installation,update & Database for phase 3 |  | 2022-10-12 | 2022-10-17
| Database infrastructure for Phase3 including TDE,ACL,Master DB /App DB user setup(Stag) | Infrastructure setup for Phase 3(Stag) |  | 2022-11-01 | 2022-11-04
| Migrate data from on-prem to AWS Phase 3(Stag) | Infrastructure setup for Phase 3(Stag) |  | 2022-11-01 | 2022-11-04
| Database infrastructure for Phase3 including TDE,ACL,Master DB /App DB user setup(Prod) | Infrastructure setup for Phase 3(Prod) |  | 2022-11-01 | 2022-11-04
| Migrate data from on-prem to AWS Phase 3(Prod) | Infrastructure setup for Phase 3(Prod) |  | 2022-11-01 | 2022-11-04
MileStone | Data Migration |  |  | 2022-09-20 | 2022-11-04
| Dev Infrastructure ready including installation,update & Database for phase 1 |  |  | 2022-09-08 | 2022-09-19
| Dev Infrastructure ready including installation,update & database for phase 2 |  |  | 2022-09-21 | 2022-09-30
| Dev Infrastructure ready including installation,update & Database for phase 3 |  |  | 2022-09-30 | 2022-10-11
MileStone | Dev Infrastructure |  |  | 2022-09-08 | 2022-10-11
| Pipeline transferred to AzDo |  |  | 2022-09-09 | 2022-10-10
| Update the build pipeline to include SonarQube |  |  | 2022-09-09 | 2022-10-10
| Update the build pipeline to include Veracode static scans |  |  | 2022-09-09 | 2022-10-10
| Update the build pipeline to include Veracode dynamic scans(Custom code) |  |  | 2022-09-09 | 2022-10-10
| Release pipeline completed |  |  | 2022-09-09 | 2022-10-10
MileStone | CI/CD Pipeline |  |  | 2022-09-09 | 2022-10-10
| Functional Test case completion |  | Ramineni, Jagan | 2022-09-30 | 2022-10-31
| Automation Test case completion |  | Ramineni, Jagan | 2022-09-30 | 2022-10-31
MileStone | Test Cases |  |  | 2022-09-30 | 2022-10-31
| Application deployment to Dev - Phase 1 |  |  | 2022-09-20 | 2022-09-29
| Application deployment to Dev - Phase 2 |  |  | 2022-10-03 | 2022-10-12
| Application deployment to Dev - Phase 3 |  |  | 2022-10-12 | 2022-10-21
| App Deployment to Dev |  |  | 2022-09-20 | 2022-10-21
| Infrastructure setup for Phase 1(Stag) |  |  | 2022-10-04 | 2022-10-07
| Infrastructure setup for Phase 1(Prod) |  |  | 2022-10-04 | 2022-10-07 | Can we provision Stag & prod togather
| Infrastructure setup for Phase 2(Stag) |  |  | 2022-10-17 | 2022-10-20
| Infrastructure setup for Phase 2(Prod) |  |  | 2022-10-17 | 2022-10-20 | Can we provision Stag & prod togather
| Infrastructure setup for Phase 3(Stag) |  |  | 2022-10-26 | 2022-10-31
| Infrastructure setup for Phase 3(Prod) |  |  | 2022-10-26 | 2022-10-31 | Can we provision Stag & prod togather
| Staging and Prod Infrastructure |  |  | 2022-10-04 | 2022-10-31
| Integrate health check to Dev environment |  |  | TBD | TBD
| Create cloudwatch dashboards for dev environment |  |  | TBD | TBD
| Enable X-Ray monitoring to Dev environment |  |  | TBD | TBD
| Enable Rum for Dev Environment |  |  | TBD | TBD
| Integrate health check to Stag environment |  |  | TBD | TBD
| Create cloudwatch dashboards for Stag environment |  |  | TBD | TBD
| Enable X-Ray monitoring to Stag environment |  |  | TBD | TBD
| Enable Rum for Stag Environment |  |  | TBD | TBD
| Integrate health check to Dev environment |  |  | TBD | TBD
| Create cloudwatch dashboards for Dev environment |  |  | TBD | TBD
| Enable X-Ray monitoring to Dev environment |  |  | TBD | TBD
| Enable Rum for Dev Environment |  |  | TBD | TBD
Monitoring Configuration
| Deploy the application to Stag - Phase 1 (TeamSite) |  |  | 2022-10-07 | 2022-10-10
| Deploy the application to Stag - Phase 2 (LiveSite Runtime Environment) |  |  | 2022-10-20 | 2022-10-21
| Deploy the application to Stag - Phase 3(Upgrade) |  |  | 2022-10-31 | 2022-11-01
| App Deployment to Staging |  |  | 2022-10-07 | 2022-11-01
| Execute functional test cases - Phase 1 |  |  | 2022-10-07 | 2022-10-11 | One func,Auto testing or we need it for every phase?
| Fix bugs from functional testing. Phase 1 |  |  | 2022-10-07 | 2022-10-11 | One func,Auto testing or we need it for every phase?
| Execute automation testing - Phase 1 |  |  | 2022-10-07 | 2022-10-11 | One func,Auto testing or we need it for every phase?
| Fix bugs from automation testing. Phase 1 |  |  | 2022-10-07 | 2022-10-11 | One func,Auto testing or we need it for every phase?
| Execute functional test cases - Phase 2 |  |  | 2022-10-13 | 2022-10-24 | One func,Auto testing or we need it for every phase?
| Fix bugs from functional testing. Phase 2 |  |  | 2022-10-13 | 2022-10-24 | One func,Auto testing or we need it for every phase?
| Execute automation testing - Phase 2 |  |  | 2022-10-13 | 2022-10-24 | One func,Auto testing or we need it for every phase?
| Fix bugs from automation testing. Phase 2 |  |  | 2022-10-13 | 2022-10-24 | One func,Auto testing or we need it for every phase?
| Execute functional test cases - Phase 3 |  |  | 2022-10-31 | 2022-11-02 | One func,Auto testing or we need it for every phase?
| Fix bugs from functional testing. Phase 3 |  |  | 2022-10-31 | 2022-11-02 | One func,Auto testing or we need it for every phase?
| Execute automation testing - Phase 3 |  |  | 2022-10-31 | 2022-11-02 | One func,Auto testing or we need it for every phase?
| Fix bugs from automation testing. Phase 3 |  |  | 2022-10-31 | 2022-11-02 | One func,Auto testing or we need it for every phase?
| App Testing |  |  | 2022-10-07 | 2022-11-02
| Execute performance testing |  |  | 2022-10-26 | 2022-11-04
| Fix issues from performance testing |  |  | 2022-10-26 | 2022-11-09
| Performance Testing |  |  | 2022-10-26 | 2022-11-09
| Identify the UAT testers |  |  | 2022-11-01 | 2022-11-11
| Send notifications to stakeholders for UAT testing |  |  | 2022-11-11 | 2022-11-11
| UAT |  |  | 2022-11-22 | 2022-11-22
| Fix UAT bugs |  |  | 2022-11-29 | 2022-11-29
| Acquire UAT Signoff |  |  | 2022-12-01 | 2022-12-01
| UAT |  |  | 2022-11-01 | 2022-12-01
| Ensure all user stories and test cases are closed. |  |  | 2022-12-01 | 2022-12-01
| Acquire QA formal signoff |  |  | 2022-12-01 | 2022-12-01
| ​QA Signoff |  |  | 2022-12-01 | 2022-12-01
| Update cutover/Rollback plan |  |  | TBD | TBD
| Create change ticket & acquire necessary approvals |  |  | 2022-11-30 | 2022-11-30
| Inform the stakeholders for outages (If Any) |  |  | 2022-12-01 | 2022-12-01
| Execute the cutover tasks/Rollback(If required) |  |  | 2022-12-08 | 2022-12-08
| Smoke testing |  |  | 2022-12-08 | 2022-12-08
| Send communication to stakeholders post deployment |  |  | 2022-12-08 | 2022-12-08
| Production Cutover |  |  | 2022-11-30 | 2022-12-08
Formulas:
Start Date = MIN(E2:[Start Date, row above])
Start Date = [End Date, row above]+1
End Date = MAX(F2:[End Date, row above])
End Date = WORKDAY([Start Date],7)

## Sustainability of Dev Countries
Task# | Task | Owner | Comments | Estimated # of days | Start Date | Target End Date | Status | % Completion | time axis 2022-11-10 to 2023-01-28
1 | Data Wrangling & Dataset finalization
1.1 | Data Discovery - understand the data definition for all the features | Aanya/Parsh | Parsh - 'level_of_development', 'greenhousegas_emissione_mtco2equivalent', 'total_government_revenue_proportion_of_gdp_perc', 'fdi_inflows_millionusd', 'annual_growth_rate_perc', 'proportion_of_population_with_primary_reliance_on_clean_fuels_a', 'mortality_rate_perc', 'renewable_energy_share_on_the_total_energy_consumption', Aanya -'co2emissions_from_fuel_combustion_in_millions_of_tonnes', 'fossilfuel_subsidies_consumption_and_production_billionusd', 'randd_expenditure_proportionofgdp_perc', 'national_action_plans_as_priority_national_policies', 'number_of_companies_publishing_sustainability_reports', 'education_for_sustainable_development', 'enhance_policy_coherence_for_sustainable_development', 'land_degraded_over_total_land_area' | 4 | 2022-11-12 | 2022-11-16 | In Progress
1.2 | Data Structuring - translate data into meaningful values as needed(Reduce dimentions,String to int,split date if needed,create bins etc) | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.3 | Data Structuring - create additional columns based on existing columns - if needed | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.4 | Data Cleaning - Remove unnecessary records(Developed nations data etc),unrelavant columns) | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.5 | Data Cleaning - find and treat outliers | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.6 | Data Cleaning - find and treat null values | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.7 | Data Cleaning - find duplicate/error values and treat them | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.8 | Data Enriching - find,discuss & finalize other dataset or create more data using Algo(Explote KNN algo for generating data) | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.9 | Data Enriching - Apply all above techniques to the new dataset (Keep the scripts & update/reuse it) | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.10 | Data Enriching - merge relavant information with the primary dataset | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
1.11 | Data Enriching - Normalize & data Levelling | Aanya/Parsh |  | 7 | 2022-11-12 | 2022-11-19 | In Progress
2 | Model Selection & Parameters Setting
2.1 | Identify dependent & independent variables (clustering ,Corelation Analysis) | Aanya/Parsh |  | 1 | 2022-11-19 | 2022-11-20 | In Progress
2.2 | Determine most important Attributes in the dataset | Aanya/Parsh |  |  |  |  | In Progress
2.3 | Select the appropriate model based on the above study (Read about different model & where they are applied) | Aanya/Parsh |  |  |  |  | In Progress
3 | Data Modelling
3.1 | Split the dataset into train & test | Aanya/Parsh |  |  |  |  | In Progress
3.2 | Train the data using the refined dataset | Aanya/Parsh |  |  |  |  | In Progress
3.3 | Check the success rate using test data (Not applicable for several unsupervised algo) | Aanya/Parsh |  |  |  |  | In Progress
3.4 | Repate the above steps with different parameters until error % is reduced. | Aanya/Parsh |  |  |  |  | In Progress
3.5 | Save the model | Aanya/Parsh |  |  |  |  | In Progress
4 | Project Wrap up
4.1 | Build a front end application to use the model (If required) | Aanya/Parsh |  |  |  |  | In Progress
4.2 | Prepare a document outlining your study and observations | Aanya/Parsh |  |  |  |  | In Progress
4.3 | Prepare the boards. | All |  |  |  |  | In Progress
5 | Others
5.1 | Preapare the document to complete the registration | All |  |  | 2022-11-16 | 2022-11-24 | In Progress

## MetaData
Col Name | Definition | Corelation with Column | Type of Corelation(H/L/M) | Cardinality(H/M/L) | Data Type(List/String/Discrete/Continuous) | Require levelling? | Acceptable Values | Comments
.dtyear
'dt_date',
'country', |  |  |  | High
'region', |  |  | H( 'total_government_revenue_proportion_of_gdp_perc',)
'level_of_development', |  |  |  |  | List of Strings |  | Least Developed' 'Not Specified' 'Economies in Transition' 'Developing Economies', 'Developed Economies'
'greenhousegas_emissione_mtco2equivalent', | Metric tons of carbon dioxide equivalent (MTCO2 Eq.) A metric measure used to compare the emissions from different greenhouse gases based upon their global warming potential (GWP). The carbon dioxide equivalent for a gas is derived by multiplying the tons of the gas by its associated GWP. In ARCHIBUS, total emissions is expressed as MTCO2 that is calculated by adding the metric tons of carbon dioxide emissions with the metric ton carbon dioxide equivalents for methane and nitrous oxide. Total Emissions (MTCO2) = Emissions MTCO2+ CH4 Emissions (MTCO2 Eq.) + N2O Emissions (MTCO2 Eq.) |  | H(fdi_inflows_millionusd) |  | Discrete
'total_government_revenue_proportion_of_gdp_perc', | This comparison provides a sense of the size of the federal government's earnings in relation to the total amount of the entire country's economic output. In fiscal year 2022, federal revenue was equal to 20% of total gross domestic product (GDP), or economic activity, of the United States that year $25.00 trillion |  | H(region) |  |  |  |  | count 1192.000000 mean 349.787220 std 1082.433384 min 0.004870 25% 14.630493 50% 65.117955 75% 315.587295 max 12300.200000
'fdi_inflows_millionusd', | FDI: Foreign Direct Investment. Investments made by a company or governement into a foreign concern. FDI Inflows are the investments that come into the nation.
'annual_growth_rate_perc', | The annual growth rate is the rate at which the nations GDP changes. It is also described as the measurment of the increase in value of a revenue stream in a given year. This rate is used to measure a nations economy(determining wether it is in recession or expansion).
'proportion_of_population_with_primary_reliance_on_clean_fuels_a', | The ratio of people primarily depending on clean fuels for certain task to the total amount of people that perform that task.
'mortality_rate_perc', | Ratio of number of deaths in the year to the average total population. Esentially Death Rate
'renewable_energy_share_on_the_total_energy_consumption', | What percent/ratio of the total consumption of energy in a nation is renewable. Ex. In the U.S. renewable energy generates 20% of the U.S electricity.
'co2emissions_from_fuel_combustion_in_millions_of_tonnes',
'fossilfuel_subsidies_consumption_and_production_billionusd',
'randd_expenditure_proportionofgdp_perc',
'national_action_plans_as_priority_national_policies', |  |  |  |  | Constant |  | 1
'number_of_companies_publishing_sustainability_reports',
'education_for_sustainable_development',
'enhance_policy_coherence_for_sustainable_development',
'land_degraded_over_total_land_area'